## Slide 2
Portfolio Management and the Framework Contract (FC4)
Utilising the FC4, in conjunction with the rest of the NEC4 suit, to accelerate delivery of Portfolios.
Prepared by ECS Associates | 5 October 2026
Arthur De Swardt
ICE-SA Jam Session
Do the right things,
not only doing things right.

## Slide 3
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Purpose of today’s session
BASIS OF THIS JAM SESSION
How can we maximise the NEC4 suite of contracts, especially the Framework Contract (FC4), to optimise the delivery of a portfolio of capital projects
3
2
1
Section title
What is Portfolio Management and what are its contracts challenges
How the NEC4 suite supports portfolio delivery
Real world example

## Slide 4
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Section 1
1
What is Portfolio Management and what are its contracts challenges

## Slide 5
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management
A Portfolio is a collection of Projects, Programmes, Portfolios and other Enterprise activities that are managed together to deliver strategic Enterprise Benefits
A Portfolio of Infrastructure capital projects is normally managed in a Portfolio Management Office (PfMO).
The PfMO normally reports to the Executive Level
A Portfolio defines:
The capital project activities that, combined, will deliver the organizational goals
Early scope and benefits of all projects
Which projects should go ahead, when and where,
How much budget should be allocated to each project
Are we doing the right things,
as well as doing things right ?
The right project at the right time with the right contract

## Slide 6
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management
What do Portfolio Managers worry about?
Are our projects continually aligned with the company strategy
If not, what are we going to do about it
Long term planning (5, 10, 15 years MTEFx3)
Is the pipeline of projects maximised
Do our service providers (Contractors, PSP’s) have enough capacity for our pipeline
Can the market service our pipeline
Project BENEFITS, not necessarily only deliverables
Project MILESTONES, not necessarily activities

## Slide 7
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Portfolios are large: SA Infrastructure Budget 2026 to 2030
Chart: 
| Public | Private
% Split 2030 | 0.46 | 0.54
Chart: 
| Public | Private
% split 2026 | 0.5 | 0.5
Key:
Total Infra Budget | 
2026 | R 700 bn
2030 | R 801bn
Accum. | R3,745 bn
Public vs Private
Source: SA Government News Agency (deputy Minister of Finance)
21%
29%
Notes: Source: SA Government News Agency (deputy Minister of Finance), 13 May 2026

## Slide 8
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management
How Portfolios, Programmes and Projects fit together
Portfolio
Sub Portfolio
Projects
Programs
Projects
Projects
Projects
Sub- Programs
Projects
Sub -Projects
Programs
Other Enterprise activities
Budgeting, planning, prioritizing, stakeholder engagement

## Slide 9
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management
Project
The Building Block
Temporary endeavor undertaken to create a unique product, service, or result. In infrastructure, it has a defined start and end date, a specific budget, and focuses on output delivery.
Programme
The Connected Benefits
A group of related projects managed in a coordinated way to obtain benefits and control that wouldn't be possible from managing them individually. It focuses on outcomes and business benefits rather than just physical outputs.
Objective: To manage interdependencies between projects and ensure the overall capability is realized.
Portfolio
The Strategic Alignment
A collection of projects, programmes, and operations grouped together to achieve strategic business or government objectives. The components of a portfolio may not be directly interdependent, but they compete for the same funding, resources, and executive attention.
Objective: To maximize the return on investment by choosing the right mix of programmes and projects aligned with high-level strategy.
Objective: To deliver a specific asset on time, within budget, and to technical specifications.
Example: Constructing a single bridge or upgrading a specific water treatment plant.
Example: A school classroom building programme.
Example: A Municipal portfolio of water, energy, roads

## Slide 10
Portfolio schedule – concerned about MILESTONES and BENEFITS

## Slide 11
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management

## Slide 12
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management
Portfolio Management Activities
Strategy & Investment Alignment
Portfolio
Optimisation & Balancing
Governance
Risk
Assurance
Monitoring, Controlling & Reporting
Portfolio aligned to your Enterprise Strategy
Portfolio aligned to your Investment plan
Portfolio adjusted annually to align to new demands
Portfolio optimised to maximise Benefits within the available Budget
Portfolio balanced to balance the demands between Departments and Programmes and Enterprise priorities
Portfolio managed according to an Enterprise-wide methodology that creates consistency and repeatability of Benefit outcomes
Clear Stage Gates to govern approvals
Checks at each Stage Gate to continually review Benefits against KPI’s
Develop Enterprise-wide Assurance Management Framework
Create 4-lines of defence
Create early warning triggers proactively deal with risks
Conduct regular reviews and audits
Develop Enterprise-wide Portfolio Risk Management Framework
Identify Risks
Analyse Risks
Develop Risk responses
Monitor and Control Risks
Ensure risk mitigation measures are built into project schedules and budgets
Agree the metrics to be monitored with Executive and Project teams
Develop Reporting KPI’s
Monitor KPI’s
Develop Reports and Dashboards
Communicate Reports and Dashboards according to an agreed cadence
Reports and Dashboards to Monitor and Control the Portfolio
Tools to align, optimise, & balance your portfolio
Portfolio Management Methodology
Handbook as a reference guide to the
Methodology
Cloud-based workflow system to institutionalise the methodology
Dashboards to provide the right intelligence reporting to each level in the Organisation
Management Information System across horizontal and vertical silo’s
Risk management Framework, tool and reporting
Assurance framework, project reviews, health checks, audit
Geographic Information System to plot your projects and create a Master Plan
Portfolio Management Deliverables

## Slide 13
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management and what are its contracts challenges
Contracts challenge # 1
Rigid project lifecycle
With such a long and rigid lifecycle, what are the chances that it remains as the right project at the place at the right time with the right budget

## Slide 14
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management and what are its contracts challenges
Contracts challenge # 2
Unrealistic budget windows
Government projects are often driven by service delivery crises and the annual budgeting cycle.
Projects are often:
Prioritized by urgent service delivery crises, and not within the broader context of infrastructure planning
The Project life cycle gets squeezed into a financial year
This generates the standard “hockey stick” effect, resulting in:
A Portfolio that is not meaningfully Prioritised
A Portfolio that is not planned for long term efficiencies
Planning and design shortcuts
Pressure to deliver construction within unrealistic timeframes (often between January to June of the financial year)
Construction short cuts
Crisis management

## Slide 15
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management and what are its contracts challenges
Contracts challenge # 3
Sequencing
Prioritising and sequencing of the projects in the portfolio to match available budget as well as project demands

## Slide 16
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
1
What is Portfolio Management and what are its contracts challenges
Contracts challenge # 3
Sequencing (contd.)
Chart: Cost million zar
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
Project 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 10 | 20 | 30 | 30
Project 3 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 20 | 35 | 35 | 45 | 45
Project 5 | 10 | 10 | 10 | 10 | 10
Project 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20 | 20 | 20 | 20 | 40 | 10 | 10 | 10
Project 7 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 50 | 50
Project 8 | 1 | 2 | 2 | 2 | 2 | 2 | 30 | 30 | 30 | 30 | 40 | 30 | 30 | 30
Project 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 20 | 20 | 20 | 20 | 40 | 40 | 40 | 40 | 0
Project 10 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Project 9 | 1 | 1 | 1 | 3 | 4 | 2 | 30 | 30 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 50 | 30 | 40 | 40 | 30 | 40
Project 4 | 40 | 40 | 40 | 40 | 60 | 60 | 60 | 60 | 70 | 50 | 50 | 50
Total Projects Cost | 12 | 14 | 13 | 15 | 56 | 48 | 74 | 74 | 73 | 74 | 93 | 94 | 104 | 131 | 131 | 132 | 123 | 133 | 104 | 107 | 98 | 68 | 8 | 3 | 23 | 4 | 24 | 25 | 58 | 58 | 88 | 88 | 87 | 97 | 67 | 67 | 67 | 53 | 97 | 96
Budget | 70 | 70 | 70 | 70 | 71 | 71 | 71 | 71 | 72 | 72 | 72 | 72 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 76 | 76 | 76 | 76 | 80 | 80 | 80 | 80 | 90 | 91 | 91 | 91 | 91 | 91 | 91 | 91

## Slide 17
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Section 2
2
How the NEC4 suite supports Portfolio delivery, especially the Framework Contract (FC4)
Acknowledgement: Richard Patterson NEC4 Framework Contract webinar

## Slide 18
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
2
How the NEC4 suite supports Portfolio delivery, especially the Framework Contract (FC4)
Acronym | Definition
PSC | Professional Service Contract
PSS | Professional Service Subcontract
ECC | Engineering and Construction Contract
ECS | Engineering and Construction Subcontract
SC | Supply Contract
TSC | Term Service Contract
TSS | Term Service Subcontract
ALC | Alliance Contract
DBO | Design, Build and Operate Contract
PSSC | Professional Service Short Contract
ECSC | Engineering and Construction Short Contract
ECSS | Engineering and Construction Short Subcontract
SSC | Supply Short Contract
TSSC | Term Service Short Contract
FC | Framework Contract
DRSC | Dispute Resolution Service Contract
The NEC4 family of contracts
Procurement strategy: who does what, when (vertical, horizontal split)
Contracting strategy: how to allocate the risk

## Slide 19
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
2
How the NEC4 suite supports Portfolio delivery, especially the Framework Contract (FC4)
Frameworks are most useful where future needs are likely, but their timing, quantity or precise location is uncertain.
One-off Contract
Unique, high-value
projects.
Defined start/end.
Specific Scope.
(ECC, ECS, DBO)
Panel / Roster
List of pre-qualified
suppliers. Often
rotational.
No guarantee of work.
Operationally rigid.
Term Service
Contract (TSC)
Continuous service
for a duration.
E.g., Cleaning,
Vegetation
Management.
Framework
Contract (FC)
Agreement to execute
FUTURE works on
instruction.
Flexible scope.
Transactional
Relational/Strategic
The landscape of procurement vehicles

## Slide 20
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
2
How the NEC4 suite supports Portfolio delivery, especially the Framework Contract (FC4)
The goal: framework contracts that are faster without becoming uncontrolled.
The Scope does not have to be detailed at Framework Stage
When the procurement cycle is longer than the work itself, the system is too slow for responsive infrastructure delivery.

## Slide 21
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
2
How the NEC4 suite supports Portfolio delivery, especially the Framework Contract (FC4)
Framework contracting = capacity first, orders later.
The FRAMEWORK (Level 1):
Framework Contract: an agreement between a Client and one or more Contractors, the purpose of which is to establish the terms governing orders to be awarded during a given period, in particular with regard to price and, where appropriate, the quantity envisaged (ISO 10845:2020)
It is • A long-term arrangement
• A way to pre-establish key terms
• A mechanism for repeat work
• A programme-level supplier strategy
It is not • A guarantee of work
• A blank cheque
• An open-ended appointment
• A substitute for proper scope definition
Value is created through issuing of orders which are read together with the framework contract
Allows repeat work
Allows for Early Supplier Involvement (ESI)
Zero value contract
The ORDERS (Level 2):
A Time Charge Order: is an instruction to provide advice on a proposed Work Order on a time charge basis.
Work Order: is a contract to carry out work within the framework scope.

## Slide 22
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
How NEC4 FC works: two levels
THE FRAMEWORK IS THE PLATFORM; EACH ORDER IS A SEPARATE CONTRACT
Level 1: NEC4 Framework Contract
NEC Framework Contract (FC)
Sets the ‘Rules of the Game’ (Contract Data Part 1 & 2)
Client + Suppliers | Client’s Representative | Framework scope | Selection procedure | Quotation procedure | Framework Information
Time Charge Order Advice, investigations, scoping, early input before a later Work Order. Usually time-based.
Work Order Separate contract to carry out work. Must be within framework scope and use order-specific documents.
The FC is the coat hanger; the orders are the contracts hanging from it.
NEC ECC
(Engineering &
Construction)
NEC ECSC
(Engineering &
Construction Short Contract)
NEC PSC
(Professional Services Contract)
NEC PSSC
(Professional Services Short Contract)
Time Charge Orders help define the problem.
Work Orders deliver the solution.
Level 2

## Slide 23
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
The NEC4 core clauses: FC compared to ECC (Eng & Construction Contr) and PSC (Prof Serv Contr)
CONTRACT STRUCTURE
Aspects
NEC4 ECC
NEC4 PSC
NEC4 FC
Parties
Client / Contractor
Client / Consultant
Client / Supplier(s)
Agent / administrator
Project Manager and Supervisor
Service Manager
Client’s Representative
1. General
Actions, communications, roles, early warning, etc.
Actions, communications, roles, early warning, etc.
Actions, communications, Client’s Representative, corrupt acts
2. Main responsibilities
Contractor’s main responsibilities
Consultant’s main responsibilities
Parties’ obligations; Supplier selection; Time Charge Order; Work Order quotation
3. Time / completion
Starting, programme, completion
Starting, programme, completion
Completion of the framework obligations
4-8
Quality, payment, compensation events, title, liabilities and insurance
Quality, payment, compensation events, rights to material, liabilities and insurance
Not used in the FC - dealt with in the individual order contract where applicable
9. Termination
Termination under the ECC
Termination under the PSC
Termination of the Framework Contract
Secondary options
Used where selected in Contract Data
Used where selected in Contract Data
Generally not used in FC; relevant options are selected in the order contract
The FC sets the framework machinery. ECC and PSC contain the detailed project/service administration machinery.

## Slide 24
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Framework timing: End Date, Time Charge Orders and Work Orders
WHEN ORDERS MAY BE PLACED AND COMPLETED
Framework start
End Date
Time Charge Order
advice / scoping
Work Order A
delivery before End Date
Work Order B
may complete after End Date if awarded before it
Work Order X
Not permitted
new order after End Date
Rule of thumb: do not award a new order after the framework End Date. An order properly placed before the End Date may have its own later Completion Date if the framework and governance documents allow it.

## Slide 25
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Project lifecycle: framework contracts
EARLIER SUPPLIER INPUT AND FASTER ORDER PLACEMENT
Advice, options and value engineering
Carry out the work
Frameworks support Early Contractor Involvement and value engineering without waiting for a full project-by-project procurement process.
8
Post implementation review
7
Close Out
6
Handover
5
Works
4
Procurement
3
Design
2
Concept
1
Strategy
Time Charge Order
Work Order
Fast track
Selection and Quotation
Defined in the FC

## Slide 26
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
When a framework is suitable
THE FRAMEWORK OPTION FITS REPEATABILITY, UNCERTAINTY AND NEED FOR RAPID MOBILISATION
Suitable Recurring category of work
Uncertain quantities, timing or locations
Need for rapid mobilisation
Programme or portfolio delivery
Scope can be defined by category
Supplier capacity must be secured
Less suitable Unique mega-project with complete scope
Requirement outside advertised framework scope
No clear selection procedure
No delegated authority or budget
Supplier capability uncertain
Used merely to avoid competition
Decision test: can the Client describe the category, selection rules and commercial basis now, even if the exact order is unknown?

## Slide 27
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Advantages of using framework contracts
WHY ORGANISATIONS CHOOSE THIS ROUTE
1
Speed Faster mobilisation once need is identified.
2
Consistency Standard commercial and contractual rules.
3
Flexibility Different order forms and pricing options.
4
Competition Mini-competition or objective allocation can retain value pressure.
5
Relationships Longer-term learning, collaboration and innovation.
6
Portfolio control Track spend, workload, performance and capacity.
7
Reduced admin Less repeated tendering and negotiation.
8
Risk management Pre-vetted capacity and repeatable documentation.
Frameworks create value by standardising what should be standard and preserving choice where the specific order needs it.

## Slide 28
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Potential South African applications
FRAMEWORKS ARE USEFUL WHEREVER THE CATEGORY REPEATS BUT THE EXACT ORDER IS NOT YET KNOWN
Public infrastructure
Schools, clinics and public buildings
Roads, stormwater and municipal works
Water and sanitation repairs
Electricity distribution infrastructure
Professional services and investigations
Disaster recovery and emergency works
Private infrastructure and industry
Mining sustaining capital
Plant shutdowns and maintenance
Commercial property portfolios
Renewable energy programmes
Telecommunications rollout
Data centres and logistics facilities
Common factor: repeated category + uncertain timing, quantity or location.

## Slide 29
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Section 3
3
Real world example

## Slide 30
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Associates
Section 3
Daily Maverick reports:
The Mayor of a major Metro in SA plans to spend … money on highly visible projects that can be completed before voters head to the polls.
The mayor has also proposed that members of the mayoral committee (MMCs) meet without top City bosses to decide which unfinished projects should be prioritised.
He proposed identifying projects needing immediate completion, securing their funding, and delaying newer initiatives. “We are 50 days away to an election”.
Statement: 1 Oct 2026
Completion: 4 November 2026
Real world portfolio delivery pressure
3

## Slide 31
Key takeaways
Portfolio Management: Do the – RIGHT THINGS, not only doing things right
Portfolios are at the ENTERPRISE level
Key contracts challenges in Portfolios are:
  Rigid project lifecycles
  Unrealistic budget windows
  Project sequencing
The FC4 provides some flexibility of contracting in Portfolios
The NEC4 suite supports Portfolio delivery
A good framework is faster because the rules are already designed.
Further reading:
Constructing the Gold Standard
An Independent Review of Public Sector Construction Frameworks
By Professor David Mosey
Centre of Construction Law, King's College London

## Slide 32
MINING & METALS | INFRASTRUCTURE | ENERGY | POWER | WATER | GAS | RENEWABLE ENERGY
ECS Professional Services
Dispute Avoidance Board Services
Social Media Advisory Services
Online Advertising
Contract Management Advisory
Claims Management
Risk Management
Expert Witness
Dispute Avoidance and Resolution
Commercial Management
Procurement and Contract Strategies
Project Management Consulting
Expert Resources
Independent Assurance
Business/Project Analysis
Capital Project Services
Technical Advisory
Internet and Internet Services
Project Management Office
Project Services
SMART Construction
Training and Development
Planning and Delay Analysis
Data Visualisation and PowerBi
Project Management
Claims & Dispute Management
Scope Management
Construction Law and Contracts
Contract (NEC, FIDIC, JBCC, GCC)
Collaboration Culture
Focus on Claims and Dispute Avoidance
$10Bn
Projects managed
800+
Cumulative Years Experience
16
Professional Affiliations
NEC
Accredited
1000+
Specialists Network
400+
Training sessions
Portfolio Management
Reporting
Controlling
Monitoring
Optimisation & balancing
Strategy Alignment
Assurance
Governance
Risk
WWW.ECS.CO.ZA