Stakeholder Engagement Plan

| Names (Individuals/Groups) | Make It Happen | Help It Happen | Let It Happen | Criticize It Happening | Stop It Happening | Why this reaction? Concerns & Needs | Strategy Who/How |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MSAs | X |  |  | √ |  | Concerned change will create extra work | Get one MSA onboard to trial the change. Demonstrate how new process will actually save time and effort |
| MSA Supervisor |  | X |  |  | √ | Need to feel part of the decision-making process | Give opportunity to present ideas; include in all planning and discussion of project |
| Providers | X | √ |  |  |  | Believe their role is supportive vs. active | Educate the providers on their role in reducing MOR & impact on clinical care |
| COS |  | X | √ |  |  | Unaware of need for more active role | Advise on role needed and how to move providers from help to make it happen |
| Nursing | √ X |  |  |  |  |  |  |

Directions:

- Identify key stakeholders.

- Place a √ in the box that best describes their current level of commitment to the change initiative.

- Place an X where you need them to be for the initiative to be successful.

- If there is a gap between the two, draw an arrow from the √ to the X. If there is no gap, circle the √.

- Where there is a gap, identify why. Indicate their concerns and needs.

- Choose a strategy for dealing with resistance to change. Identify who is responsible.