## Slide 1: Communication Planning

## Slide 2: Development of a Communication Process
Effective Communications
Must have the following characteristics:
  A consistent formal process
  Simple and understood by all
  Contain current information
  Have a feedback loop built into the process
Will help:
  Build and maintain trust
  Prevent rumors
  Enlist and enroll the participation of employees in the pursuit of achieving objectives

## Slide 3: How Will You Communicate?
What is the best way to communicate with your team, key stakeholders, and project sponsor?
  Who is your audience?
  What is the tool or media you will use to communicate?
  What is the purpose of your communication?
  What are your key messages?
  Who is the owner of the communications task?
  What is the timing and frequency of the communications?

## Slide 4: Communication Plan Development
1. Determine audience and media to be used
2. Complete a Communication Plan
3. Complete a Stakeholder Analysis

## Slide 5: 1. Determine Audience and Media
Identify the various audiences you will need to communicate to:
   Executive Team  Departmental Managers  Administration
   Risk Management  Sales  Marketing
   HR  Consumer Relations  Engineering
   Resource Management  Legal  Customers
   Salaried  Hourly  Marketplace
   South America  Distributors  Europe
   Asia  North America
Identify the media by which you will communicate to the groups above:
   Voice Mail  E-Mail  Posters
   Memos  Oral Communication  Formal Presentations
   “Elevator Speech”

## Slide 6: 2. Complete Communication Plan
Comes in many forms, but Key Elements include:
  Target of communication
  Frequency of communication
  Media to be used
  Be specific,
    Example 1: A 30 minute verbal conversation, every Friday at 4 p.m., including topics …
    Example 2: A weekly written update, to be completed by Friday end-of-day, to include, a) Activities completed this past week, b) activities to be completed next week, c) current risk to on-time, on-budget completion, and d) action plan to resolve risks
Revise, as necessary, as project matures
  Especially important to revise/update for project implementation
Obtain verbal agreement on each plan element from target of communication

## Slide 7: p. 2: Road map Define - Inverse Grayscale Communications Plan Example
Project Sponsor | Power Steering E-mail | Status Update | Project Status | Belt | Weekly | Establish common format
Process Owner | Power Steering E-mail | Status Update | Project Status | Belt | Monthly | Establish common format
Project Team | Power Steering Meeting | Project Progress | Tasks and Issues | Belt | Weekly | Regularly scheduled mtgs. to be cancelled as needed.
Deployment Director | Power Steering | Status Update | Tollgate | Project Sponsor | As needed | Project Progress on/off track
Audience
Media
Purpose
Topics of Discussion/
Key Messages
Owner
Frequency
Notes/Status

## Slide 8: 3. Complete a Stakeholder Analysis
For each Stakeholder identified, determine:
  Are they critical for development of project tasks (Project Enabling Stakeholders) or critical for the successful implementation of a solution (Project Implementation Stakeholders)?
  What concerns can you anticipate for each Stakeholder?
  What positive outcomes exist for each Stakeholder?
  What will be your message for each Stakeholder?
A Stakeholder Analysis should be completed/revised as critical aspects of the project change (I.e. scope changes, solution options become more visible, etc.)
A Stakeholder Analysis should be a confidential document

## Slide 9: Stakeholder Analysis Example
Stakeholder
Name/Group
Project Impact
On
Stakeholder
(H=9, M=3, L=1)
Stakeholder
Influence Level
On Project
Success
(H=9,M=3,L=1)
Stakeholder’s
Current Attitude
Toward Project
( +, 0, - )
Explanation of
Current
Stakeholder
Attitude
(list)
Stakeholder
Score
(Impact x
Influence x
Attitude)
HIARNG (Hawaii Army National Guard) | H | H | + | Undergoing Reset year 1 – focus is transforming into an IBCT | 81 | Implement results as soon as available
AKARNG (Alaskan Army National Guard) | H | H | - | Scheduled for ARFORGEN 4Q this FY | -81 | Implement results in 2008
GUARNG (Guam Army National Guard) | H | H | 0 | Scheduled for ARFORGEN next FY | 0 | Implement results in 2008
USARPAC (US Army Reserves Pacific) | L | M | + | Favorable – want to work ICW TSC-P / ODT | 3 | Implement results as soon as available
Action Plan
For
Stakeholder
Key: ICW = In Conjunction With TSC-P = Training Support Center – Pacific ODT = Overseas Deployment Training
Notes: Stakeholder Score is a multiplication of Impact, Influence, and Attitude; similar to the Risk Priority Number of a FMEA. Range -81 to +81
Examples:
Impact H (9) x Influence M (3) x Attitude 0 (0) = (9x3x0) = Score 0
Impact L (1) x Influence L (1) x Attitude + (1) = (1x1x1) = Score 1
Impact M (3) x Influence H (9) x Attitude – (-1) = (3x9x-1) = Score = -27
Score Interpretations/Recommended Actions:
+81: This stakeholder is one that the project team needs to keep on their side! Keep them informed of the project status at all times. Enlist this stakeholder to help drive the project to higher levels and aid in influencing the (-) negative stakeholders.
+27: The project team also needs to keep this stakeholder on their side. Keep them informed of the project status at all times. Can the project team work to get this stakeholder's score up to +100?
0: This stakeholder currently is "not interested" in the project. Keep this stakeholder informed and brief them on all the positive aspects of this project. Do not let this stakeholder become against your project.
-27: Caution! This stakeholder has the potential to derail your project. Keep them informed and try to determine why they have a negative attitude toward your project.
-81: Danger! This stakeholder could easily derail your project! This stakeholder will prevent you and your project team from achieving the full amount of success that you could.
Determine if this stakeholder will be against your project no matter what. If so, and especially if this is your training project, put this project back in the project hopper and get a new project.
NOTE to Instructors: Previous versions had H=3, M=2, L=1 and +=1, 0=2 and -=3. Current version with 9, 3, and 1 is consistent with other scoring methods and distinguishes between positive and negative stakeholders.

## Slide 10: Communications Exercise
Goal – Establish a communications plan for your project using the communication plan template
Time Limit – 10 Minutes
Be prepared to share your plan with the table group and receive feedback on your plan