## Budget
Project Cost Estimate (High)
|  | # Hrs. | Cost/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1.1 | Design Phase |  |  |  | 6400 | 14.95%
1.1.1 | Site Design/ Templates | 64 | 50 | 3200
1.1.2 | Graphic Design | 48 | 50 | 2400
1.1.3 | Initial Design Approval | 16 | 50 | 800
1.2 | Content Phase |  |  |  | 8800 | 20.56%
1.2.1 | Define and Gather Critical Content | 120 | 50 | 6000
1.2.2 | Copy Editing and Proofing | 40 | 50 | 2000
1.2.3 | Initial Copy Approval | 16 | 50 | 800
1.3 | Build/ Integrate Phase |  |  |  | 12000 | 28.04%
1.3.1 | Integrate Graphics into Templates | 80 | 50 | 4000
1.3.2 | Integrate Copy into Templates | 160 | 50 | 8000
1.4 | Test and Update Phase |  |  |  | 10800 | 25.23%
1.4.1 | Launch Draft Website, Gather Feedback | 16 | 50 | 800
1.4.2 | Modify Draft based on Feedback | 80 | 50 | 4000
1.4.3 | Launch Draft Website, Gather Feedback | 80 | 50 | 4000
1.4.4 | Modify Draft based on Feedback | 40 | 50 | 2000
1.5 | Launch Phase |  |  |  | 4800 | 11.21%
1.5.1 | Prepare Website for launch | 80 | 50 | 4000
1.5.2 | Launch Website on Public Server | 16 | 50 | 800
Total Project Cost Estimate |  |  |  |  | 42800
Summary
> The only identifiable cost involved in this project is the cost of labor. > All of the hours expended on the project will be at the overtime rate. > Since each individual has a different pay rate, this worksheet shows a high estimate based on the average rate. > The number of hours indicated are also a high estimate; based upon survey taken from the team's projections.