## EV data
Earned Value Calculations for Project Name
Prepared by: |  |  | Date:
Note: Change the entries to meet your project needs. This data is from Figure 7-4 of Schwalbe's text Information Technology Project Management, Fourth Edition.
Also make sure the formulas work properly based on the data you enter.
[13 empty] | To Date | Planned | Actual
Activity | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | PV | % Complete | % Complete | RV | EV
Plan and staff project | 4000 | 4000 | [10 empty] | 8000 | 100 | 100 | 100% | 8000
Analyze requirements |  | 6000 | 6000 | [9 empty] | 12000 | 100 | 100 | 100% | 12000
Develop ERDs |  |  | 4000 | 4000 | [8 empty] | 8000 | 100 | 100 | 100% | 8000
Design database tables |  |  |  | 6000 | 4000 | [7 empty] | 10000 | 100 | 100 | 100% | 10000
Design forms, reports, and queries |  |  |  |  | 8000 | 4000 | [6 empty] | 8000 | 75 | 50 | 66.67% | 5333.3333
Construct working prototype | [5 empty] | 10000 | [7 empty] | 0 |  |  | 0
Test/evaluate prototype | [5 empty] | 2000 | 6000 | [6 empty] | 0 |  |  | 0
Incorporate user feedback | [6 empty] | 4000 | 6000 | 4000 |  |  |  |  | 0 |  |  | 0
Test system | [8 empty] | 4000 | 4000 | 2000 |  |  | 0 |  |  | 0
Document system | [10 empty] | 3000 | 1000 |  | 0 |  |  | 0
Train users | [11 empty] | 4000 |  | 0 |  |  | 0
Monthly Planned Value (PV) | 4000 | 10000 | 10000 | 10000 | 12000 | 16000 | 10000 | 6000 | 8000 | 4000 | 5000 | 5000 |  |  |  |  | 43333.3333
Cumulative Planned Value (PV) | 4000 | 14000 | 24000 | 34000 | 46000 | 62000 | 72000 | 78000 | 86000 | 90000 | 95000 | 100000
Monthly Actual Cost (AC) | 4000 | 11000 | 11000 | 12000 | 15000
Cumulative Actual Cost (AC) | 4000 | 15000 | 26000 | 38000 | 53000
Monthly Earned Value (EV) | 4000 | 10000 | 10000 | 10000 | 9333.3333
Cumulative Earned Value (EV) | 4000 | 14000 | 24000 | 34000 | 43333.3333
Project EV as of May 31 | 43333.3333
Project PV as of May 31 | 46000
Project AC as of May 31 | 53000
CV=EV-AC | -9666.6667
SV=EV-PV | -2666.6667
CPI=EV/AC | 81.76%
SPI=EV/PV | 94.2%
Estimate at Completion (EAC) | 122307.6923 | (original plan of $100,000 divided by CPI)
Estimated time to complete | 12.7385 | (original plan of 12 months divided by SPI)