## START HERE
MWC MASTER CLOUD ASSESSMENT & MIGRATION QUESTIONNAIRE
ASSESS FIRST. MIGRATE SECOND.
Purpose | A professional discovery and assessment workbook for conducting a structured Cloud Assessment & Migration across business, application, infrastructure, security, operations, cost, and migration-readiness domains.
How to use | Work through the MASTER QUESTIONNAIRE with the appropriate stakeholders. Record responses, evidence, owners, risks, follow-up actions, and architect notes. Use the Dashboard and Domain Summary to track progress.
Method | DISCOVER → MAP → ASSESS → OPTIMIZE → MIGRATE
Question Library | 240 curated questions across 16 assessment domains.
Important | This workbook is a generalized MWC assessment product. Client-specific names, hostnames, IPs, credentials, and confidential data from source materials are not included.
Response workflow | 1) Ask question 2) Record response 3) Validate evidence 4) Flag risk/follow-up 5) Assign owner/action 6) Close the gap
Completion logic | A question counts as complete when Status is set to Complete. Use Not Applicable only when the question truly does not apply to the assessed scope.
Recommended evidence | Architecture diagrams, inventories, CMDB exports, monitoring reports, policies, contracts, SLA/OLA records, DR test results, backup/restore evidence, cost reports, and migration plans.
WORKBOOK NAVIGATION
Dashboard | Executive progress and readiness view
MASTER QUESTIONNAIRE | Complete assessment question library and working responses
Domain Summary | Completion, risk, and follow-up counts by domain
Risks & Follow-Ups | Working action register for material findings
Evidence Tracker | Track requested evidence and validation status
LOOKUPS | System configuration values used by workbook dropdowns. Do not edit unless you intentionally want to change the standardized selections.
Version | MWC Master Cloud Assessment & Migration Questionnaire ¦ Version 1.0 ¦ © 2026 Modernize Without Compromise
License | Licensed for use by the purchaser. Redistribution, resale, repackaging, or publication of this workbook or its question library is not permitted without written authorization from Modernize Without Compromise.
Customer Input | Enter assessment data only in the designated response, evidence, owner, risk, follow-up, action, notes, date, and status fields. Dashboard and Domain Summary are reporting views.
Configuration | The LOOKUPS worksheet supports standardized dropdown values and workbook logic. It is intended as system configuration rather than an assessment working sheet.

## MASTER QUESTIONNAIRE
Question ID | Phase | Domain | Subdomain | Discovery Question | Why It Matters | Required / Optional | Target Audience | Target Level | Response Type | Response | Evidence Required | Evidence / Source | Evidence Date | Owner | Priority | Risk / Concern | Follow-Up Required | Follow-Up Action | Architect Notes | Source Basis | Status
BUS-001 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What business drivers are behind the cloud initiative? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-002 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What business outcomes are expected from the cloud initiative? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-003 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What is the approved scope of the assessment and migration? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-004 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What business units, services, applications, and locations are in scope? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-005 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What major timeline expectations and milestones have been established? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-006 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What known business constraints could affect the migration timeline or approach? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-007 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What major business changes or planned initiatives could affect the technology environment during migration? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-008 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | Which business services are considered most critical to the organization? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-009 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What is the business impact if each critical service becomes unavailable? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-010 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What risk thresholds or outage tolerances have been defined for critical business areas? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Required | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-011 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | Are there regulatory, audit, or contractual deadlines that influence the migration schedule? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Recommended | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-012 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What business growth assumptions should the target environment support? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Recommended | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-013 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What current pain points or service limitations are expected to be improved through migration? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Recommended | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-014 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | What success criteria will be used to determine whether the migration achieved its intended outcomes? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Recommended | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
BUS-015 | DISCOVER | Business Strategy & Migration Drivers | Strategy & Outcomes | Who has authority to approve material changes to migration scope, schedule, or business priorities? | Establishes business intent, scope, timing, and decision criteria that constrain the migration. | Recommended | Business Sponsor / Program Lead | Executive / Business | Document / Interview |  | Business case, scope, roadmap, approved milestones |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-001 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Who is the executive sponsor for the cloud assessment and migration? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-002 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Who are the primary business stakeholders for the in-scope services and applications? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-003 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Who are the technical owners for the in-scope applications and infrastructure? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-004 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Is a current organization chart available for the IT and support teams involved in scope? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-005 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | How are technology teams divided by work responsibility and location? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-006 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | What key services are provided by each in-scope technology team? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-007 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | What skill sets are required to support the current environment? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-008 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Are the required subject matter experts available to participate in discovery and validation? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-009 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Which support functions are performed by contractors, managed service providers, or other third parties? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-010 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | What current operating and support model is used for the in-scope environment? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Required | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-011 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | How are IT priorities aligned with business priorities and governance? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Recommended | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-012 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Is an enterprise architecture or architecture governance practice currently in place? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Recommended | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-013 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Who owns final decisions for architecture, security, operations, and migration readiness? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Recommended | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-014 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | What escalation paths exist for unresolved technical or business decisions? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Recommended | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
ORG-015 | DISCOVER | Organization, Stakeholders & Governance | Ownership & Operating Model | Which vendors or third parties must participate in discovery, testing, cutover, or post-migration support? | Clarifies ownership, governance, required SMEs, and accountability for decisions and support. | Recommended | Program Lead / IT Leadership | Executive / Management | Document / Interview |  | Org chart, RACI, support model, vendor list |  |  |  | High |  | No |  |  | MWC Readiness Checklist + Enterprise Due Diligence | Not Started
CUR-001 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Are current architecture diagrams available for the in-scope environment? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-002 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Do the architecture diagrams show network, web, application, database, storage, and load-balancing components? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-003 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Are separate DEV, TEST/QA, UAT, and PROD environments documented where applicable? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-004 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Are application integration and dependency diagrams available? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-005 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Is a validated application inventory available? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-006 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Is a validated server and infrastructure inventory available? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-007 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Is a validated database inventory available? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-008 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Is a current network topology or LAN/WAN diagram available? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-009 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Is the identity and directory-services architecture documented? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-010 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Are storage, backup, monitoring, and disaster-recovery architectures documented? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-011 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Is a CMDB or other authoritative configuration repository available? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-012 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | How accurate and current are the existing inventory and configuration records? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-013 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Are assets identified by environment, location, condition, and ownership? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-014 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | Has current-state information been validated against evidence rather than accepted without review? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
CUR-015 | DISCOVER | Current-State Architecture & Documentation | Architecture Evidence | What major documentation gaps must be resolved before migration design can be finalized? | Provides evidence of the actual current state and exposes documentation or inventory gaps. | Required | Enterprise / Solution Architect | Architect / SME | Document / Evidence |  | Architecture diagrams, inventories, CMDB extracts |  |  |  | Critical |  | No |  |  | All four supplied workbooks | Not Started
APP-001 | ASSESS | Application Portfolio & Business Criticality | Application Profile | How many applications and workloads are in scope? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-002 | ASSESS | Application Portfolio & Business Criticality | Application Profile | What business function does each application support? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-003 | ASSESS | Application Portfolio & Business Criticality | Application Profile | Who is the business owner for each application? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-004 | ASSESS | Application Portfolio & Business Criticality | Application Profile | Who is the technical owner or production support owner for each application? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-005 | ASSESS | Application Portfolio & Business Criticality | Application Profile | What is the business criticality of each application? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-006 | ASSESS | Application Portfolio & Business Criticality | Application Profile | What service level agreement or operational level agreement applies to each application? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-007 | ASSESS | Application Portfolio & Business Criticality | Application Profile | What are the normal operating hours and peak usage periods for each application? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-008 | ASSESS | Application Portfolio & Business Criticality | Application Profile | How many users consume each application and where are those users located? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-009 | ASSESS | Application Portfolio & Business Criticality | Application Profile | Is downtime permitted for each application, and if so, how much? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-010 | ASSESS | Application Portfolio & Business Criticality | Application Profile | Is each application custom-developed, commercial off-the-shelf, ERP, infrastructure, or another application type? | Determines workload importance, ownership, service expectations, and lifecycle context. | Required | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-011 | ASSESS | Application Portfolio & Business Criticality | Application Profile | Which applications are considered the primary systems supporting critical business processes? | Determines workload importance, ownership, service expectations, and lifecycle context. | Recommended | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-012 | ASSESS | Application Portfolio & Business Criticality | Application Profile | Are any applications currently being upgraded or materially changed? | Determines workload importance, ownership, service expectations, and lifecycle context. | Recommended | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-013 | ASSESS | Application Portfolio & Business Criticality | Application Profile | Are any applications or software components out of vendor support or approaching end of support? | Determines workload importance, ownership, service expectations, and lifecycle context. | Recommended | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-014 | ASSESS | Application Portfolio & Business Criticality | Application Profile | What is the lifecycle status of each application: strategic, maintain, modernize, replace, retire, or unknown? | Determines workload importance, ownership, service expectations, and lifecycle context. | Recommended | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
APP-015 | ASSESS | Application Portfolio & Business Criticality | Application Profile | What audit, compliance, or regulatory requirements apply to each application? | Determines workload importance, ownership, service expectations, and lifecycle context. | Recommended | Application Owner | Business / Application SME | Text / Choice |  | Application inventory, SLA/OLA, owner records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-001 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | What architecture pattern does each application use: two-tier, three-tier, n-tier, batch, or another pattern? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-002 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | What application layers or components make up the solution? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-003 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | What operating systems, middleware, runtimes, web servers, application servers, and other technologies make up the technology stack? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-004 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | How do users interact with the application: web, client, API, batch, or another method? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-005 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | Is the application internet-facing, intranet-facing, or both? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-006 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | What environments exist for the application: DEV, TEST/QA, UAT, PROD, DR, or others? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-007 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | Is a lower environment sufficiently similar to production for migration testing? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-008 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | Is lower-environment data volume representative enough to support meaningful testing? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-009 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | Is the application deployed on physical servers, virtual machines, containers, or another platform? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-010 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | Is clustering or another high-availability configuration used? | Defines how the application is built and deployed so migration requirements can be assessed. | Required | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-011 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | What load-balancing technologies and configurations are used? | Defines how the application is built and deployed so migration requirements can be assessed. | Recommended | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-012 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | Are custom routing policies, proxy services, or reverse proxies part of the architecture? | Defines how the application is built and deployed so migration requirements can be assessed. | Recommended | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-013 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | What file systems, shared file systems, and mount points are required? | Defines how the application is built and deployed so migration requirements can be assessed. | Recommended | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-014 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | What scheduling or batch-processing components are part of the application architecture? | Defines how the application is built and deployed so migration requirements can be assessed. | Recommended | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
ARC-015 | ASSESS | Application Architecture & Technology Stack | Deployment Architecture | Is the application engineering team available to perform required configuration and validation during migration? | Defines how the application is built and deployed so migration requirements can be assessed. | Recommended | Application Architect / SME | Architect / Technical SME | Text / Choice |  | Architecture and deployment diagrams, configuration records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + Enterprise Due Diligence | Not Started
DEP-001 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What upstream systems does each application depend on? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-002 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What downstream systems depend on each application? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-003 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | Is each dependency another application, shared service, DNS, directory service, email, SMS, database, file system, or other component? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-004 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | Is each dependency internal or provided by a third party? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-005 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What type of integration is used for each dependency: API, database link, file transfer, mount point, messaging, batch feed, or another method? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-006 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What source and destination systems participate in each integration? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-007 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What ports and protocols are required for each dependency? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-008 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What DNS, routing, proxy, or name-resolution requirements exist for each dependency? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-009 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What volume of data is transferred through each integration? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-010 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What are the normal timing, frequency, and scheduling requirements for each data flow? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-011 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | Are there external feeds or batch dependencies that can delay or block processing? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-012 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | Which dependencies are migration-critical? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-013 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | Which dependent systems must be included in the same migration move group or wave? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-014 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | What happens if a dependency is unavailable or connectivity is interrupted during migration? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
DEP-015 | MAP | Integrations, Dependencies & Data Flows | Dependency Mapping | Have application owners validated the documented dependency map and data flows? | Identifies coupling, connectivity, sequencing, and move-group requirements that can affect cutover. | Required | Application / Integration Architect | Architect / Technical SME | Text / Matrix |  | Dependency diagrams, interface inventory, flow records |  |  |  | Critical |  | No |  |  | Application Discovery + Migration Portfolio + MWC Readiness Checklist | Not Started
CMP-001 | ASSESS | Compute & Server Infrastructure | Server Discovery | How many servers are in scope by site, environment, and application? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-002 | ASSESS | Compute & Server Infrastructure | Server Discovery | What host name and infrastructure identifier is used for each server? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-003 | ASSESS | Compute & Server Infrastructure | Server Discovery | Is each server physical or virtual? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-004 | ASSESS | Compute & Server Infrastructure | Server Discovery | What hypervisor or virtualization platform is used where applicable? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-005 | ASSESS | Compute & Server Infrastructure | Server Discovery | What operating system and version is installed on each server? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-006 | ASSESS | Compute & Server Infrastructure | Server Discovery | What CPU count and CPU speed are allocated to each server? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-007 | ASSESS | Compute & Server Infrastructure | Server Discovery | What are the average and peak CPU utilization levels? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-008 | ASSESS | Compute & Server Infrastructure | Server Discovery | How much RAM is allocated to each server? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-009 | ASSESS | Compute & Server Infrastructure | Server Discovery | What are the average and peak memory utilization levels? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-010 | ASSESS | Compute & Server Infrastructure | Server Discovery | How much disk capacity is allocated and utilized by each server? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Required | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-011 | ASSESS | Compute & Server Infrastructure | Server Discovery | What are the average and peak IOPS requirements where available? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Recommended | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-012 | ASSESS | Compute & Server Infrastructure | Server Discovery | Are any servers clustered or configured for high availability? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Recommended | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-013 | ASSESS | Compute & Server Infrastructure | Server Discovery | What is the server patch-management process and how frequently are updates applied? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Recommended | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-014 | ASSESS | Compute & Server Infrastructure | Server Discovery | What maintenance windows and availability requirements apply to each environment? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Recommended | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CMP-015 | ASSESS | Compute & Server Infrastructure | Server Discovery | Are there documented server shutdown and restart procedures that account for application dependencies? | Establishes the compute baseline, capacity profile, support state, and infrastructure constraints. | Recommended | Infrastructure / Server SME | Technical SME | Number / Text |  | Server inventory, monitoring/utilization reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-001 | ASSESS | Database & Data | Database Discovery | What database engines are used by the in-scope applications? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-002 | ASSESS | Database & Data | Database Discovery | What database versions are currently deployed? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-003 | ASSESS | Database & Data | Database Discovery | What operating systems or platforms host the databases? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-004 | ASSESS | Database & Data | Database Discovery | What is the size of each database? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-005 | ASSESS | Database & Data | Database Discovery | What is the daily or periodic data-growth rate for each database? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-006 | ASSESS | Database & Data | Database Discovery | What type of data is stored in each database? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-007 | ASSESS | Database & Data | Database Discovery | What retention policies apply to the data? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-008 | ASSESS | Database & Data | Database Discovery | Which databases support ERP or other business-critical applications? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-009 | ASSESS | Database & Data | Database Discovery | Who is the DBA or technical owner for each database? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-010 | ASSESS | Database & Data | Database Discovery | What database monitoring tools are currently used? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Required | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-011 | ASSESS | Database & Data | Database Discovery | What backup and recovery strategy is used for each database? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Recommended | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-012 | ASSESS | Database & Data | Database Discovery | What RPO and RTO requirements apply to each production database? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Recommended | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-013 | ASSESS | Database & Data | Database Discovery | Are any databases currently being upgraded or materially changed? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Recommended | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-014 | ASSESS | Database & Data | Database Discovery | Are any database versions out of vendor support or approaching end of support? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Recommended | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
DAT-015 | ASSESS | Database & Data | Database Discovery | Are diagrams or documentation available showing application-to-database integrations and dependencies? | Establishes database technology, scale, recovery, ownership, and lifecycle requirements. | Recommended | DBA / Data SME | Technical SME | Text / Number |  | Database inventory, backup records, monitoring reports |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-001 | MAP | Network & Connectivity | Network Discovery | Are current LAN/WAN diagrams available for all in-scope locations? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-002 | MAP | Network & Connectivity | Network Discovery | What network equipment and appliances support connectivity for the in-scope environment? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-003 | MAP | Network & Connectivity | Network Discovery | Are any network devices running unsupported software revisions or approaching end of support? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-004 | MAP | Network & Connectivity | Network Discovery | What IP addressing and subnetting schemes are used? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-005 | MAP | Network & Connectivity | Network Discovery | What VLANs and network segments are used by the in-scope applications and infrastructure? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-006 | MAP | Network & Connectivity | Network Discovery | What firewall platforms and firewall rules apply to the in-scope systems? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-007 | MAP | Network & Connectivity | Network Discovery | What inbound and outbound source, destination, port, and protocol requirements exist? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-008 | MAP | Network & Connectivity | Network Discovery | What DNS services, zones, forwarders, and name-resolution dependencies are used? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-009 | MAP | Network & Connectivity | Network Discovery | What DHCP services or other shared network services are required? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-010 | MAP | Network & Connectivity | Network Discovery | What WAN technologies and leased connectivity services are used between locations? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Required | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-011 | MAP | Network & Connectivity | Network Discovery | What bandwidth is available between relevant sites, data centers, cloud connectivity points, and DR locations? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Recommended | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-012 | MAP | Network & Connectivity | Network Discovery | How is high availability implemented for network and internet connectivity? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Recommended | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-013 | MAP | Network & Connectivity | Network Discovery | Are quality-of-service, traffic-priority, filtering, or routing policies required? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Recommended | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-014 | MAP | Network & Connectivity | Network Discovery | What tools are used to manage and monitor LAN/WAN infrastructure? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Recommended | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
NET-015 | MAP | Network & Connectivity | Network Discovery | What network changes or firewall changes are expected to be required for migration? | Defines connectivity, addressing, security boundaries, bandwidth, and network changes required. | Recommended | Network Architect / SME | Architect / Technical SME | Text / Matrix |  | Network diagrams, firewall rules, circuit inventory |  |  |  | Critical |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-001 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | What storage technologies are used: local disk, SAN, NAS, object storage, or others? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-002 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | What allocated and utilized storage capacity exists for each in-scope storage platform? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-003 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | What average and peak IOPS requirements are known? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-004 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | What file-system, volume, mount-point, or shared-storage dependencies exist? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-005 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | Is storage multipathing or redundant connectivity used where required? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-006 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | What storage monitoring and capacity-reporting tools are used? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-007 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | Is there clearly defined and tested backup and restore documentation? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-008 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | What types of backups are performed and on what schedule? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-009 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | Are all production and non-production environments backed up as required? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-010 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | What tools are used to back up servers, applications, databases, and file data? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Required | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-011 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | When was the last successful restore test performed and what evidence is available? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Recommended | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-012 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | What retention and aging policies apply to backed-up data? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Recommended | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-013 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | Is backup data encrypted and how are encryption keys managed? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Recommended | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-014 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | Are backup copies stored off-site or in a separate failure domain, and how are they tracked? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Recommended | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
STO-015 | ASSESS | Storage, Backup & Data Protection | Storage & Backup | How frequently are backup and restore procedures reviewed and updated through change control? | Defines capacity, performance, protection, retention, and recovery requirements for data. | Recommended | Storage / Backup SME | Technical SME | Text / Number |  | Storage reports, backup policies, restore-test evidence |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
SEC-001 | ASSESS | Identity, Security & Compliance | Security & Identity | Is a current information-security policy documented, approved, and published? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-002 | ASSESS | Identity, Security & Compliance | Security & Identity | Are information-security responsibilities clearly assigned? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-003 | ASSESS | Identity, Security & Compliance | Security & Identity | Have third-party connection and access risks been assessed? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-004 | ASSESS | Identity, Security & Compliance | Security & Identity | Are security requirements included in relevant third-party and outsourcing contracts? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-005 | ASSESS | Identity, Security & Compliance | Security & Identity | Is an inventory of major information assets maintained? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-006 | ASSESS | Identity, Security & Compliance | Security & Identity | Are data-classification and information-handling requirements defined? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-007 | ASSESS | Identity, Security & Compliance | Security & Identity | What identity, authentication, authorization, and privileged-access controls apply to the in-scope environment? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-008 | ASSESS | Identity, Security & Compliance | Security & Identity | What Active Directory forests, domains, organizational units, and group policies support the environment? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-009 | ASSESS | Identity, Security & Compliance | Security & Identity | What directory, DNS, PKI, certificate, or other identity-related shared services are required? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-010 | ASSESS | Identity, Security & Compliance | Security & Identity | How are privileged and administrative accounts controlled and monitored? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-011 | ASSESS | Identity, Security & Compliance | Security & Identity | Is encryption required for data in transit and/or at rest? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-012 | ASSESS | Identity, Security & Compliance | Security & Identity | Are any proprietary encryption mechanisms used by the applications? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-013 | ASSESS | Identity, Security & Compliance | Security & Identity | What compliance, regulatory, and audit requirements apply to the in-scope systems and data? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-014 | ASSESS | Identity, Security & Compliance | Security & Identity | Are audit trails and security-relevant logs produced and retained for investigation and compliance needs? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
SEC-015 | ASSESS | Identity, Security & Compliance | Security & Identity | What security incident reporting, response, and escalation procedures are currently in place? | Defines identity, access, policy, encryption, compliance, and audit controls that must be preserved. | Required | Security / IAM Lead | Security / Technical SME | Text / Yes-No |  | Security policies, IAM design, audit/compliance evidence |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + MWC Readiness Checklist | Not Started
DR-001 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | Is there a documented and formally approved disaster-recovery plan? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-002 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | When was the DR plan last tested? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-003 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | How frequently are DR plans and scenarios tested? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-004 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | Are results and evidence from previous DR tests available? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-005 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | What production systems and applications are included in DR scope? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-006 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | What RTO and RPO requirements apply to each critical application and service? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-007 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | What is the business impact of failure for each critical application? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-008 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | How is service maintained during a failure or disaster event? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-009 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | Is an alternate method of conducting business defined if service cannot be restored within the required timeframe? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-010 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | What recovery capabilities are required from critical third-party service providers? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-011 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | Where is the recovery site located and is it active, standby, active-active, or active-passive? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-012 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | What replication method is used between production and recovery environments? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-013 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | What network bandwidth and connectivity are available between primary and recovery locations? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-014 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | What support is required from application and infrastructure teams during DR tests or failover? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
DR-015 | ASSESS | Availability, DR & Business Continuity | Resilience & Recovery | Are DR roles, responsibilities, escalation contacts, and minimum recovery resources clearly defined? | Defines availability and recovery expectations and validates whether recovery capabilities are proven. | Required | DR / Business Continuity Lead | Management / Technical SME | Text / Date |  | DR plan, test results, RTO/RPO records |  |  |  | Critical |  | No |  |  | Enterprise Due Diligence + Migration Portfolio + MWC Readiness Checklist | Not Started
OPS-001 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What monitoring tools are used for applications, hosts, storage, databases, and networks? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-002 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | To what degree is monitoring automated? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-003 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | Are monitoring tools integrated with ticket creation, paging, or escalation processes? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-004 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What service-level requirements apply to monitoring and operational support? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-005 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | Are standard operating procedures documented and available for the in-scope systems? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-006 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What regular operational checklists and recurring activities are performed? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-007 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What scheduling packages or batch-processing tools are used? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-008 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What external batch feeds or dependencies can affect operational processing? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-009 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What known busy periods, month-end, quarter-end, or year-end processing requirements exist? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-010 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What automation tools are currently used by operations? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Required | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-011 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What incident, problem, change, release, and configuration-management processes are in place? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Recommended | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-012 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What are the scheduled maintenance, change, and release windows? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Recommended | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-013 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What tools are used for ITSM, CMDB, asset management, change management, and reporting? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Recommended | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-014 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What operational reports, dashboards, and service reports are currently produced? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Recommended | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
OPS-015 | ASSESS | Operations, Monitoring & Service Management | Operational Readiness | What post-migration support ownership, escalation paths, and handoff requirements must be established? | Defines how the environment is monitored, operated, changed, supported, and handed over after migration. | Recommended | Operations / Service Management Lead | Management / Technical SME | Text / Choice |  | SOPs, ITSM reports, monitoring dashboards |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
LIC-001 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | What commercial and open-source software products are used by each in-scope application? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-002 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | What software version is currently deployed for each licensed product? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-003 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | What license type and license count apply to each product and environment? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-004 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Can existing licenses be transferred or ported to the target cloud environment? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-005 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Does the vendor support the software on the intended target cloud or platform? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-006 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Will a different license type or entitlement be required after migration? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-007 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Are any software products currently outside vendor support? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-008 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Which vendor maintenance or support contracts apply to the in-scope hardware and software? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-009 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Which third parties provide managed services or operational support? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-010 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | What vendor or third-party SLAs apply to the in-scope services? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Required | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-011 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | What leased hardware, software, WAN, or connectivity services are in scope? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Recommended | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-012 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Who are the key suppliers for the in-scope technology environment? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Recommended | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-013 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Are there contract renewal, termination, or notice dates that could constrain migration timing? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Recommended | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-014 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | Are there procurement policies or approval processes that could affect acquisition of migration or cloud services? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Recommended | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
LIC-015 | ASSESS | Licensing, Vendors & Commercial Constraints | Licensing & Vendor Support | What vendor dependencies must be resolved before cutover or decommissioning can occur? | Identifies licensing, support, contract, vendor, and procurement constraints that can block or change migration. | Recommended | Vendor / Licensing / Procurement Lead | Management / Commercial SME | Text / Date |  | License inventory, contracts, support agreements |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence | Not Started
CST-001 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What current operating and capital costs are associated with the in-scope environment? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-002 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What hardware, software, support, maintenance, connectivity, and managed-service costs are in scope? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-003 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What average and peak CPU utilization is observed for the in-scope servers? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-004 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What average and peak memory utilization is observed for the in-scope servers? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-005 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What allocated versus utilized disk and storage capacity exists? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-006 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What average and peak IOPS requirements are observed for storage and servers? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-007 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What network bandwidth and utilization levels are observed during normal and peak periods? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-008 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | Which servers, applications, databases, or storage platforms are materially underutilized? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-009 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | Which systems have known capacity constraints or performance bottlenecks? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-010 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What server or infrastructure refresh activity is expected within the next 12 to 24 months? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Required | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-011 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | Which applications or infrastructure components are candidates for retirement or consolidation? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Recommended | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-012 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | Which environments operate continuously even when business usage does not require 24x7 availability? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Recommended | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-013 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What backup, retention, and archive requirements materially influence storage consumption? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Recommended | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-014 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What licensing models could materially change cost after migration? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Recommended | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
CST-015 | OPTIMIZE | Cost, Utilization & Optimization | Utilization & Cost Drivers | What cost risks or optimization opportunities should be evaluated before the target architecture is finalized? | Creates the utilization and cost baseline needed to identify sizing, retirement, and optimization opportunities. | Recommended | FinOps / Infrastructure Lead | Management / Technical SME | Number / Text |  | Cost reports, utilization reports, contracts |  |  |  | High |  | No |  |  | Migration Portfolio + Enterprise Due Diligence + MWC Readiness Checklist | Not Started
MIG-001 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | Has a migration approach been identified for each in-scope application or workload? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-002 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What technical or business constraints could prevent an application from migrating as planned? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-003 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | Which applications and dependencies must be migrated in the same move group or wave? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-004 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What migration wave or sequence is proposed for each application? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-005 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | Are DEV, TEST/QA, UAT, and PROD migration approaches defined separately where required? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-006 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | Is a lower environment available to validate migration procedures before production cutover? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-007 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What application, infrastructure, database, network, security, and vendor changes are required before migration? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-008 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What firewall, routing, DNS, certificate, or connectivity changes are required for cutover? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-009 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What downtime window is permitted for migration of each production application? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-010 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What data-migration, replication, synchronization, or final-delta requirements exist? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-011 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | Who is responsible for application testing and business signoff after migration? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-012 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What rollback or backout criteria and procedures are required? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-013 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What cutover dependencies, sequencing requirements, and go/no-go decisions must be documented? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-014 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What post-migration monitoring, support, and stabilization activities are required? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started
MIG-015 | MIGRATE | Migration Readiness, Strategy & Constraints | Migration Planning | What unresolved risks, pending information, or decisions must be closed before the workload is considered migration-ready? | Converts discovery into executable sequencing, cutover, validation, rollback, and readiness decisions. | Required | Migration Lead / Solution Architect | Architect / Program Lead | Text / Choice |  | Migration plan, wave plan, cutover/rollback plan |  |  |  | Critical |  | No |  |  | Migration Portfolio + Application Discovery + MWC Readiness Checklist | Not Started

## Domain Summary
MWC DOMAIN ASSESSMENT SUMMARY
Domain | Total Questions | Complete | In Progress | Not Started | Follow-Ups | Completion %
Business Strategy & Migration Drivers | 15 | 0 | 0 | 15 | 0 | 0%
Organization, Stakeholders & Governance | 15 | 0 | 0 | 15 | 0 | 0%
Current-State Architecture & Documentation | 15 | 0 | 0 | 15 | 0 | 0%
Application Portfolio & Business Criticality | 15 | 0 | 0 | 15 | 0 | 6.667%
Application Architecture & Technology Stack | 15 | 0 | 0 | 15 | 0 | 0%
Integrations, Dependencies & Data Flows | 15 | 0 | 0 | 15 | 0 | 6.667%
Compute & Server Infrastructure | 15 | 0 | 0 | 15 | 0 | 0%
Database & Data | 15 | 0 | 0 | 15 | 0 | 0%
Network & Connectivity | 15 | 0 | 0 | 15 | 0 | 0%
Storage, Backup & Data Protection | 15 | 0 | 0 | 15 | 0 | 0%
Identity, Security & Compliance | 15 | 0 | 0 | 15 | 0 | 0%
Availability, DR & Business Continuity | 15 | 0 | 0 | 15 | 0 | 0%
Operations, Monitoring & Service Management | 15 | 0 | 0 | 15 | 0 | 0%
Licensing, Vendors & Commercial Constraints | 15 | 0 | 0 | 15 | 0 | 0%
Cost, Utilization & Optimization | 15 | 0 | 0 | 15 | 0 | 6.667%
Migration Readiness, Strategy & Constraints | 15 | 0 | 0 | 15 | 0 | 6.667%

## Dashboard
MWC CLOUD ASSESSMENT & MIGRATION DASHBOARD
KPI | Value | Phase | Questions | Complete | Follow-Ups | Completion %
Total Questions | 240 | DISCOVER | 45 | 0 | 0 | 0%
Complete | 0 | MAP | 30 | 0 | 0 | 0%
Follow-Ups Required | 0 | ASSESS | 135 | 0 | 0 | 0%
Overall Completion | 0% | OPTIMIZE | 15 | 0 | 0 | 0%
|  | MIGRATE | 15 | 0 | 0 | 0%

## Risks & Follow-Ups
RISKS & FOLLOW-UPS ACTION REGISTER
Action ID | Question ID | Domain | Risk / Finding | Follow-Up Action | Owner | Priority | Due Date | Status | Closure Notes
ACT-001 | [7 empty] | Open
ACT-002 | [7 empty] | Open
ACT-003 | [7 empty] | Open
ACT-004 | [7 empty] | Open
ACT-005 | [7 empty] | Open
ACT-006 | [7 empty] | Open
ACT-007 | [7 empty] | Open
ACT-008 | [7 empty] | Open
ACT-009 | [7 empty] | Open
ACT-010 | [7 empty] | Open
ACT-011 | [7 empty] | Open
ACT-012 | [7 empty] | Open
ACT-013 | [7 empty] | Open
ACT-014 | [7 empty] | Open
ACT-015 | [7 empty] | Open
ACT-016 | [7 empty] | Open
ACT-017 | [7 empty] | Open
ACT-018 | [7 empty] | Open
ACT-019 | [7 empty] | Open
ACT-020 | [7 empty] | Open
ACT-021 | [7 empty] | Open
ACT-022 | [7 empty] | Open
ACT-023 | [7 empty] | Open
ACT-024 | [7 empty] | Open
ACT-025 | [7 empty] | Open
ACT-026 | [7 empty] | Open
ACT-027 | [7 empty] | Open
ACT-028 | [7 empty] | Open
ACT-029 | [7 empty] | Open
ACT-030 | [7 empty] | Open
ACT-031 | [7 empty] | Open
ACT-032 | [7 empty] | Open
ACT-033 | [7 empty] | Open
ACT-034 | [7 empty] | Open
ACT-035 | [7 empty] | Open
ACT-036 | [7 empty] | Open
ACT-037 | [7 empty] | Open
ACT-038 | [7 empty] | Open
ACT-039 | [7 empty] | Open
ACT-040 | [7 empty] | Open
ACT-041 | [7 empty] | Open
ACT-042 | [7 empty] | Open
ACT-043 | [7 empty] | Open
ACT-044 | [7 empty] | Open
ACT-045 | [7 empty] | Open
ACT-046 | [7 empty] | Open
ACT-047 | [7 empty] | Open
ACT-048 | [7 empty] | Open
ACT-049 | [7 empty] | Open
ACT-050 | [7 empty] | Open
ACT-051 | [7 empty] | Open
ACT-052 | [7 empty] | Open
ACT-053 | [7 empty] | Open
ACT-054 | [7 empty] | Open
ACT-055 | [7 empty] | Open
ACT-056 | [7 empty] | Open
ACT-057 | [7 empty] | Open
ACT-058 | [7 empty] | Open
ACT-059 | [7 empty] | Open
ACT-060 | [7 empty] | Open
ACT-061 | [7 empty] | Open
ACT-062 | [7 empty] | Open
ACT-063 | [7 empty] | Open
ACT-064 | [7 empty] | Open
ACT-065 | [7 empty] | Open
ACT-066 | [7 empty] | Open
ACT-067 | [7 empty] | Open
ACT-068 | [7 empty] | Open
ACT-069 | [7 empty] | Open
ACT-070 | [7 empty] | Open
ACT-071 | [7 empty] | Open
ACT-072 | [7 empty] | Open
ACT-073 | [7 empty] | Open
ACT-074 | [7 empty] | Open
ACT-075 | [7 empty] | Open
ACT-076 | [7 empty] | Open
ACT-077 | [7 empty] | Open
ACT-078 | [7 empty] | Open
ACT-079 | [7 empty] | Open
ACT-080 | [7 empty] | Open
ACT-081 | [7 empty] | Open
ACT-082 | [7 empty] | Open
ACT-083 | [7 empty] | Open
ACT-084 | [7 empty] | Open
ACT-085 | [7 empty] | Open
ACT-086 | [7 empty] | Open
ACT-087 | [7 empty] | Open
ACT-088 | [7 empty] | Open
ACT-089 | [7 empty] | Open
ACT-090 | [7 empty] | Open
ACT-091 | [7 empty] | Open
ACT-092 | [7 empty] | Open
ACT-093 | [7 empty] | Open
ACT-094 | [7 empty] | Open
ACT-095 | [7 empty] | Open
ACT-096 | [7 empty] | Open
ACT-097 | [7 empty] | Open
ACT-098 | [7 empty] | Open
ACT-099 | [7 empty] | Open
ACT-100 | [7 empty] | Open

## Evidence Tracker
ASSESSMENT EVIDENCE TRACKER
Evidence ID | Domain | Evidence / Artifact | Requested From | Request Date | Received Date | Validation Status | Location / Link | Notes
EVD-001 | Current-State Architecture & Documentation | Current-state architecture diagrams |  |  |  | Not Requested
EVD-002 | Current-State Architecture & Documentation | Application inventory |  |  |  | Not Requested
EVD-003 | Current-State Architecture & Documentation | Server / infrastructure inventory |  |  |  | Not Requested
EVD-004 | Database & Data | Database inventory |  |  |  | Not Requested
EVD-005 | Network & Connectivity | Network / LAN-WAN diagrams |  |  |  | Not Requested
EVD-006 | Network & Connectivity | Firewall rules / connectivity matrix |  |  |  | Not Requested
EVD-007 | Identity, Security & Compliance | Security policies and standards |  |  |  | Not Requested
EVD-008 | Identity, Security & Compliance | Identity / Active Directory architecture |  |  |  | Not Requested
EVD-009 | Availability, DR & Business Continuity | Disaster-recovery plan |  |  |  | Not Requested
EVD-010 | Availability, DR & Business Continuity | Latest DR test results |  |  |  | Not Requested
EVD-011 | Storage, Backup & Data Protection | Backup policy and schedules |  |  |  | Not Requested
EVD-012 | Storage, Backup & Data Protection | Restore-test evidence |  |  |  | Not Requested
EVD-013 | Operations, Monitoring & Service Management | Monitoring dashboards / reports |  |  |  | Not Requested
EVD-014 | Operations, Monitoring & Service Management | ITSM incident/change/problem reports |  |  |  | Not Requested
EVD-015 | Application Portfolio & Business Criticality | Application SLA / OLA records |  |  |  | Not Requested
EVD-016 | Integrations, Dependencies & Data Flows | Application dependency / integration diagrams |  |  |  | Not Requested
EVD-017 | Licensing, Vendors & Commercial Constraints | Software license inventory |  |  |  | Not Requested
EVD-018 | Licensing, Vendors & Commercial Constraints | Vendor support / maintenance contracts |  |  |  | Not Requested
EVD-019 | Cost, Utilization & Optimization | Infrastructure utilization reports |  |  |  | Not Requested
EVD-020 | Cost, Utilization & Optimization | Current cost / budget reports |  |  |  | Not Requested
EVD-021 | Migration Readiness, Strategy & Constraints | Migration wave plan |  |  |  | Not Requested
EVD-022 | Migration Readiness, Strategy & Constraints | Cutover and rollback plan |  |  |  | Not Requested

## Source Mapping
MWC COMMERCIAL VERSION 1.0
Reserved | Development source-mapping content has been removed from the customer-facing workbook.
Note | This worksheet is not used by the assessment, dashboard, formulas, or reporting.

## LOOKUPS
Status | Priority | Follow-Up | Required / Optional | Phase | Evidence Status
Not Started | Critical | No | Required | DISCOVER | Not Requested
In Progress | High | Yes | Recommended | MAP | Requested
Complete | Medium |  |  | ASSESS | Received
Not Applicable | Low |  |  | OPTIMIZE | Validated
|  |  |  | MIGRATE | Rejected / Update Needed