## START HERE
MWC Solution Architecture Design Workbook
Version 1.0 — Commercial Edition ¦ Modernize Without Compromise ¦ Discovery-to-Design working system
Purpose
This workbook converts discovery findings into a traceable solution architecture. Use it after assessment/discovery and before detailed migration execution. Core traceability: Discovery Finding → Requirement → Architecture Decision → TO-BE Component → Risk/Dependency → Migration Handoff → Approval.
Recommended Workflow
1 | Capture business and technical drivers | Drivers & Success
2 | Confirm scope, exclusions and constraints | Scope & Constraints
3 | Convert discovery findings into design requirements | Design Requirements
4 | Document AS-IS, transition and TO-BE architecture | AS-IS / Transition / TO-BE
5 | Complete detailed technical design domains | App / Platform / Network / Security / Data / HA-DR
6 | Record major architecture decisions and trade-offs | Architecture Decisions
7 | Track risks, assumptions, issues, dependencies and exceptions | RAIDE & Dependencies
8 | Prepare architecture-to-migration handoff | Migration Handoff
9 | Complete governance review and sign-off | Approval & Sign-Off
Commercial Use Guidance
Replace or clear all yellow example rows before client use. Maintain consistent IDs across sheets. The MWC diagrams are illustrative examples, not implementation recommendations. Replace them with project-specific architecture. Do not embed proprietary customer/employer material unless you are authorized to use it. The Dashboard is a management view; detailed worksheets remain the source of record.
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Unauthorized resale or redistribution prohibited.

## Dashboard
Architecture Dashboard
Executive view of design progress, decision status, risk exposure and migration readiness
Total Requirements |  | Approved Decisions |  | Open RAIDE Items | Handoff Ready
1 |  | 0 |  | 1 | 0
SAMPLE DATA NOTE — Dashboard counts include the yellow example records until those rows are replaced or cleared.
Requirement Status |  | Decision Status
Status | Count | Status | Count
Not Started | 1 | Proposed | 1
In Progress | 0 | Under Review | 0
Blocked | 0 | Approved | 0
Complete | 0 | Rejected | 0
Traceability Reminder: Discovery Finding → Requirement → Architecture Decision → TO-BE Component → RAIDE → Migration Handoff → Approval
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Replace yellow example content before client use.

## Architecture Overview
Architecture Overview
High-level summary of the solution, architecture scope and target outcome
Project / Initiative
Customer / Business Unit
Lead Architect
Architecture Version | 1.0
Assessment Reference
Primary Cloud / Platform
Secondary Cloud / Platform
Target Completion Date
Architecture Pattern
Primary Business Outcome
Current State Summary
Transition State Summary
Target State Summary
Key Constraints
Critical Dependencies
Key Risks
Architecture Status | Draft
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Drivers & Success
Business & Technical Drivers
Capture why the solution exists and how success will be measured.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Driver ID | Driver Type | Business / Technical Driver | Rationale | Success Measure | Target / Threshold | Priority | Owner | Source / Evidence | Status
DRV-001 | Business | Reduce data center dependency | SAMPLE — Reduce legacy hosting dependency and support planned facility exit. | 100% target workloads moved | By target date | High |  |  | Not Started
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Scope & Constraints
Scope & Constraints
Define boundaries and limitations that shape the architecture.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Item ID | Category | Scope Item / Constraint | Classification | Business Impact | Technical Impact | Owner | Target Date | Source / Evidence | Status
SCP-001 | Timeline | Facility exit deadline | Constraint | SAMPLE — Exit date creates a fixed delivery milestone. | Architecture must support phased delivery |  |  |  | Open
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Design Requirements
Design Requirements
Translate discovery findings into measurable architecture requirements.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Requirement ID | Discovery Finding / Source | Requirement Statement | Domain | Requirement Type | Priority | Acceptance Criteria | Owner | Decision ID | TO-BE Component ID | Status | Evidence / Notes
REQ-001 | SAMPLE discovery finding | Production service requires defined recovery objectives | HA/DR | Availability | Critical | Approved RTO/RPO documented |  | DEC-001 | TGT-001 | Not Started | Example only
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## AS-IS Architecture
AS-IS Architecture
Document the validated current-state architecture and known gaps.
Use this sheet as the structured component register. Review the 'AS-IS Diagram' tab for the visual example, then replace the example with your project-specific architecture and reference it in the Diagram Reference / Link column.
Component ID | Domain | Component / Service | Environment | Current / Target Technology | Region / Location | Network Zone | Dependencies | Requirement IDs | Decision ID | Diagram Reference / Link | Status
CUR-001 | Application | Customer Portal Web Tier | Production | Windows Server 2019 | Primary Data Center | DMZ | Load Balancer; App Tier |  |  | AS-IS Diagram | Validated
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Transition Architecture
Transition Architecture
Document the temporary hybrid / migration-state architecture.
Use this sheet as the structured component register. Review the 'Transition Diagram' tab for the visual example, then replace the example with your project-specific architecture and reference it in the Diagram Reference / Link column.
Component ID | Domain | Component / Service | Environment | Current / Target Technology | Region / Location | Network Zone | Dependencies | Requirement IDs | Decision ID | Diagram Reference / Link | Status
TRN-001 | Network | Hybrid Private Connectivity | Production | Private circuit / VPN | Data Center ↔ Cloud | Hybrid Edge | On-prem routing; Cloud transit | REQ-001 | DEC-001 | Transition Diagram | Defined
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## TO-BE Architecture
TO-BE Architecture
Document the approved target-state architecture and target components.
Use this sheet as the structured component register. Review the 'TO-BE Diagram' tab for the visual example, then replace the example with your project-specific architecture and reference it in the Diagram Reference / Link column.
Component ID | Domain | Component / Service | Environment | Current / Target Technology | Region / Location | Network Zone | Dependencies | Requirement IDs | Decision ID | Diagram Reference / Link | Status
TGT-001 | Application | SAMPLE Target Component | Production | Cloud-native service |  |  |  | REQ-001 | DEC-001 |  | Planned
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## App & Integration
Application & Integration Design
Capture application tiers, interfaces, APIs, external systems and dependency behavior.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Design ID | Application / Service | Layer / Tier | Interface / Integration | Protocol / Port | Source | Destination | Dependency Type | Availability Need | Security Requirement | Requirement IDs | Decision ID | Status
APP-001 | Customer Portal | API | Customer Profile API | HTTPS / 443 | Web Tier | Application Tier | Hard | High | TLS; authenticated service access | REQ-001 | DEC-001 | Draft
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Infrastructure & Platform
Infrastructure & Platform Design
Define compute, runtime, platform, sizing, scaling and management design.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Design ID | Workload / Component | Platform Type | OS / Runtime | Sizing Basis | CPU / vCPU | Memory GB | Storage GB | Scaling Model | Management Tooling | Requirement IDs | Decision ID | Status
INF-001 | Application Tier | VM | Linux | Current utilization + growth | 4 | 16 | 200 | Auto Scale | Central monitoring | REQ-001 | DEC-001 | Draft
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Network & Connectivity
Network & Connectivity Design
Define segmentation, addressing, routing, DNS, hybrid connectivity and traffic controls.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Design ID | Network Component | Cloud / Site | VPC / VNet / Segment | Subnet / VLAN | CIDR / Address Space | Routing | DNS | Connectivity Type | Firewall / ACL Requirement | Ports / Protocols | Requirement IDs | Decision ID | Status
NET-001 | Production VPC | AWS | Prod VPC | Private App Subnet | 10.0.20.0/24 | Transit routing | Private DNS | Direct Connect | Restrict to required app flows | HTTPS / 443 | REQ-001 | DEC-001 | Draft
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Security & IAM
Security & IAM Design
Define identity, access, encryption, monitoring and compliance controls.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Control ID | Security Domain | Control / Requirement | Identity / Role | Authentication | Authorization | Encryption | Logging / Monitoring | Compliance Mapping | Owner | Requirement IDs | Decision ID | Status
SEC-001 | IAM | Least-privilege application access | Application Service Role | Federated / workload identity | Role-based policy | At rest + in transit | Centralized security logging | Internal security standard | Security Team | REQ-001 | DEC-001 | Draft
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Data DB & Storage
Data, Database & Storage Design
Define target data platforms, storage, protection, replication and residency.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Design ID | Data / Database Component | Technology | Data Classification | Capacity / Size | Performance Need | Replication | Backup / Retention | Encryption | Residency / Region | Requirement IDs | Decision ID | Status
DAT-001 | Customer Database | Managed relational database | Confidential | 500 GB | High transaction throughput | Multi-AZ + cross-region | Daily backup / policy retention | KMS-managed encryption | Primary + DR region | REQ-001 | DEC-001 | Draft
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## HA DR & Resiliency
HA, DR & Resiliency Design
Define availability, recovery objectives, failover patterns and resilience validation.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Resiliency ID | Application / Service | Criticality | Availability Target | RTO | RPO | HA Pattern | DR Pattern | Failover Type | Test Frequency | Monitoring / Alerting | Requirement IDs | Decision ID | Status
RES-001 | Customer Portal | Tier 1 | 99.95% | 4 hours | 15 minutes | Multi-AZ | Cross-region warm standby | Orchestrated | Semiannual | Central monitoring + alerting | REQ-001 | DEC-001 | Draft
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Architecture Decisions
Architecture Decision Register
Record major choices, alternatives, rationale and approval state.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Decision ID | Decision Title | Design Domain | Requirement IDs | Problem / Context | Options Considered | Selected Option | Decision Rationale | Impact / Trade-off | Status | Owner | Approver | Decision Date | Review Date
DEC-001 | SAMPLE Architecture Decision | HA/DR | REQ-001 | Example context | Option A; Option B | Option A | Example rationale | Example trade-off | Proposed
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## RAIDE & Dependencies
RAIDE & Dependencies
Track Risks, Assumptions, Issues, Dependencies and Exceptions that affect design and delivery.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
RAIDE ID | Type | Domain | Description | Related Requirement / Decision | Probability | Impact | Severity | Mitigation / Action | Status | Owner | Due Date | Dependency Owner | Notes
RAI-001 | Risk | HA/DR | SAMPLE risk — recovery design approval may delay handoff. | REQ-001 / DEC-001 | Medium | High | High | Define mitigation | Open |  |  |  | Example only
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Migration Handoff
Architecture-to-Migration Handoff
Translate approved design into the information the migration team needs to plan execution.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Handoff ID | TO-BE Component ID | Application / Service | Migration Strategy | Recommended Wave | Prerequisites | Dependencies | Testing Requirement | RTO / RPO Consideration | Rollback Consideration | Owner | Readiness | Target Date | Notes
HND-001 | TGT-001 | SAMPLE Service | Replatform | Wave 1 | Approved target design | Network and identity ready | Functional + failover test | Use approved RTO/RPO | Rollback to source |  | Not Ready |  | Example only
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## Approval & Sign-Off
Architecture Approval & Sign-Off
Record review, governance, conditions and final architecture approval.
Use one row per record. Link records using the ID fields so requirements, decisions, target components, risks and migration handoff remain traceable.
Approval ID | Artifact / Domain | Version | Reviewer / Approver | Role | Review Status | Decision / Comments | Conditions / Actions | Approval Date | Next Review Date | Evidence / Link | Final Status
APR-001 | Target Architecture | 1.0 | Architecture Review Board | Approver | Submitted | Example: review target-state design | Close open security action before final approval |  |  | Architecture review record | Pending
© 2026 Modernize Without Compromise ¦ MWC Solution Architecture Design Workbook ¦ Version 1.0 Commercial Edition ¦ Yellow rows are examples.

## SHEET GUIDE
MWC SOLUTION ARCHITECTURE DESIGN WORKBOOK — SHEET GUIDE
Use this guide to understand what every worksheet is for, what to enter, and how it connects to the architecture lifecycle.
Sheet | Purpose | What to Enter | Key Components | Example
START HERE | Explains the workbook workflow and traceability model. | Review before starting. | Recommended workflow; traceability chain; commercial-use guidance. | Begin here before entering project data.
Dashboard | Provides an executive view of architecture progress and readiness. | No primary data entry; metrics are driven from working sheets. | Requirement status; approved decisions; open RAIDE; handoff readiness. | Use during architecture reviews and status meetings.
Architecture Overview | Summarizes the solution at a high level. | Project, customer, architect, cloud/platform, architecture status and state summaries. | Current state; transition state; target state; risks; constraints. | Cloud migration architecture for a business application portfolio.
Drivers & Success | Captures why the architecture is being created and how success is measured. | Business, technical, regulatory, operational and financial drivers. | Driver; rationale; measure; threshold; priority; owner. | Reduce data-center dependency by the target exit date.
Scope & Constraints | Defines architecture boundaries and limitations. | In-scope, out-of-scope, constraints and assumptions. | Scope item; classification; impacts; owner; evidence. | Facility exit deadline is a project constraint.
Design Requirements | Turns discovery findings into measurable architecture requirements. | Requirements, acceptance criteria, priority and traceability IDs. | Requirement ID; domain; decision ID; TO-BE component ID; status. | Production database requires an approved RPO.
AS-IS Diagram | Shows an MWC example current-state architecture. | Replace the example with the project-specific current-state diagram. | Users; network entry; on-prem environments; tiers; DR/replication. | Dallas primary data center with secondary-site replication.
AS-IS Architecture | Stores the structured component register behind the current-state diagram. | Current components, technologies, locations, dependencies and diagram references. | Component ID; domain; environment; technology; dependency; status. | Current production web server running Windows Server.
Transition Diagram | Shows an MWC example intermediate/hybrid migration architecture. | Replace the example with the project-specific transition-state diagram. | Remaining on-prem; cloud accounts; connectivity; migration paths; temporary dependencies. | Rehost app servers while database is replatformed.
Transition Architecture | Stores structured components that exist during migration. | Temporary and hybrid components plus requirement/decision links. | Component ID; domain; technology; dependencies; diagram reference. | Temporary private connectivity between data center and cloud.
TO-BE Diagram | Shows an MWC example final target-state architecture. | Replace the example with the approved project-specific target diagram. | Regions; AZs; VPCs; tiers; security; scaling; DR; shared services. | Multi-AZ production with secondary-region DR.
TO-BE Architecture | Stores the structured target architecture component register. | Approved target components and their traceability links. | Component ID; domain; technology; dependencies; requirement IDs; decision ID. | Managed database target linked to REQ-001 and DEC-001.
App & Integration | Defines application tiers, interfaces and dependencies. | Apps, services, integrations, ports/protocols, source/destination and security needs. | Layer; interface; protocol; dependency type; availability. | API integration from web tier to application service over HTTPS.
Infrastructure & Platform | Defines compute, runtime, sizing and platform design. | VM/container/PaaS choices, OS/runtime, sizing and scaling. | Platform type; CPU; memory; storage; scaling; tooling. | Auto-scaled application tier on cloud compute.
Network & Connectivity | Defines segmentation, addressing, routing and hybrid connectivity. | VPC/VNet, subnets, CIDRs, DNS, routes, connectivity and firewall needs. | Network component; address space; routing; connectivity; ports. | Private connectivity from data center to cloud transit network.
Security & IAM | Defines identity, access, encryption and compliance controls. | IAM roles, authentication, authorization, encryption, logging and mappings. | Security domain; control; identity; encryption; monitoring. | Least-privilege application role with centralized logging.
Data DB & Storage | Defines database, data and storage architecture. | Technology, classification, capacity, performance, replication, backup and residency. | Data component; replication; retention; encryption; region. | Managed relational database with encrypted backups.
HA DR & Resiliency | Defines availability and disaster-recovery architecture. | Criticality, availability target, RTO, RPO, HA/DR pattern and testing. | RTO; RPO; failover; test frequency; monitoring. | Tier-1 service with multi-AZ HA and cross-region DR.
Architecture Decisions | Records major design decisions and their rationale. | Context, alternatives, selected option, trade-offs, owner and approval. | Decision ID; options; rationale; impact; status; approver. | Select managed database instead of self-managed VM database.
RAIDE & Dependencies | Tracks Risks, Assumptions, Issues, Dependencies and Exceptions. | Description, probability, impact, severity, mitigation, owner and due date. | RAIDE ID; type; severity; mitigation; status. | Network circuit lead time is a migration dependency.
Migration Handoff | Transfers approved architecture information into migration planning. | Migration strategy, wave, prerequisites, dependencies, tests, rollback and readiness. | Handoff ID; TO-BE component; strategy; wave; readiness. | Replatform database in Wave 2 after replication validation.
Approval & Sign-Off | Records architecture governance and final approval. | Reviewers, comments, conditions, dates and final status. | Artifact/domain; approver; review status; evidence; final status. | Security architecture approved with one follow-up action.
PRODUCT INFO | Identifies the commercial edition, version, copyright and usage notices. | Review before distributing or using the workbook with client data. | Version; publisher; example-content notice; IP notice; distribution notice. | Confirm Version 1.0 and replace example content before client use.

## AS-IS Diagram
MWC AS-IS ARCHITECTURE — CURRENT STATE
Purpose: Establish the validated current-state baseline before transformation. Replace this MWC example with your project-specific AS-IS architecture.
MWC EXAMPLE DIAGRAM — Replace with your project-specific architecture.

## Transition Diagram
MWC TRANSITION ARCHITECTURE — INTERMEDIATE STATE
Purpose: Show the temporary hybrid/intermediate state while workloads, data and dependencies move. Replace this MWC example with your project-specific transition architecture.
MWC EXAMPLE DIAGRAM — Replace with your project-specific architecture.

## TO-BE Diagram
MWC TO-BE ARCHITECTURE — TARGET STATE
Purpose: Show the approved future-state architecture after migration/transformation. Replace this MWC example with your project-specific TO-BE architecture.
MWC EXAMPLE DIAGRAM — Replace with your project-specific architecture.

## PRODUCT INFO
MWC SOLUTION ARCHITECTURE DESIGN WORKBOOK — PRODUCT INFO
Commercial Edition ¦ Version 1.0 ¦ © 2026 Modernize Without Compromise
Product | MWC Solution Architecture Design Workbook
Version | 1.0 — Commercial Edition
Publisher | Modernize Without Compromise
Copyright | © 2026 Modernize Without Compromise
Purpose | A reusable working system for translating discovery findings into traceable solution architecture and migration handoff information.
Example Content | Yellow rows and MWC diagrams are illustrative examples. Replace or clear them before client use.
Architecture Diagrams | AS-IS, Transition, and TO-BE diagrams are examples only and are not implementation recommendations.
Client / Employer IP | Only include proprietary material when you have authorization to use it.
Distribution Notice | Unauthorized resale or redistribution of this workbook is prohibited. Any additional purchase/license terms provided by the seller also apply.